## 2024 Actions
Bishops Lydeard & Cothelstone Parish Council Action Tracker
Action Point | PC Meeting | Meeting Minutes Reference | Action | Responsibility | Target Completion Date | Comments | Status | Date Completed
AP1 |  | 005/24 | Contact SALC re councillors email addresses and domain name | Clerk | 2024-01-31 |  | Closed | 2024-01-15
AP2 |  | 007/24a | Arrange for grit bins to be filled and one bin replaced | Clerk | 2024-01-31 | SC Council contacted | Closed | 2024-01-15
AP3 |  | 007/24b | Arrange for rubbish collection from the carpark | Clerk | 2024-01-31 | SC Council contacted | Closed | 2024-01-19
Ref SWT578828520
AP4 |  | 007/24c | Drains to be cleaned on A358 to prevent possible flooding | Clerk | 2024-01-31 | SC Council contacted | Closed | 2024-01-19
Ref 698225
AP5 |  | 007/24d | Whiskey Trail footpath to be filled with stone | Clerk | 2024-01-31 | On agenda 14/2/24 | Closed | 2024-02-02
AP6 |  | 008/24 | Planning 06/23/0036 Support but with expression of concern over car parking | Clerk | 2024-01-19 |  | Closed | 2024-01-16
AP7 |  | 009/24 | Quantock Vale surgery to dispense drugs - support the application | Clerk | 2024-01-19 |  | Closed | 2024-01-16
AP8 |  | 010/24 | Contact PCSO for more information on police report | Clerk | 2024-01-19 | Not possible due to GDPR | Closed | 2024-01-31
AP9 |  | 011/24 | Arrange for Somerset Gazette to be ordered for the library | Clerk | 2024-01-19 |  | Closed | 2024-01-15
AP10 |  | 012/24 | Response to AGAR queries | Chair/Clerk | 2024-02-13 |  | Closed | 2024-02-05
AP11 |  | 044/24 | Defribrillator for school (£500) - agenda for meeting 14/2/24 | Clerk | 2024-02-10 |  | Closed | 2024-01-15
AP12 |  | 043/24 | Carpet cleaning Library (£100 quote awaited) - agenda 14/2/24 | Clerk | 2024-02-05 |  | Closed | 2024-02-13
AP13 |  | 026/24 | Website and email addresses proposal | Clerk | 2024-03-10 |  | Closed | 2024-02-27
AP14 |  | 032/24 | Proposal for scoping exercise on youth provision in the village | P Durban | 2024-04-10 |  | Open
AP15 |  | 032/24 | Establish Working Party on flood risk and prevention | Cllr Orr | 2024-04-10 | Deferred to 11/12/2024 | Closed
AP16 |  | 037/24 | Reports on road and traffic issues to be submitted to Somerset Council | Chair | 2024-03-10 |  | Closed | 2024-02-19
AP17 |  | 037/24 | Report on CIL funds and fixed assets | Clerk | 2024-03-10 |  | Closed | 2024-02-26
AP18 |  | 037/24 | Report on possible acquisition of Ash Priors Common | Cllr Rigby | 2024-03-10 | See AP70 | Closed
AP19 |  | 045/24 | Follow up on fly tipping on Broadgate | Clerk | 2024-03-10 | Email | Closed | 2024-02-20
AP20 |  | 045/24 | Query time taken to clear rubbish in the underpass | Clerk | 2024-03-10 | Email | Closed | 2024-02-20
AP21 |  | 045/24 | Ask Lengthsman to stain the notice board on Greenway | Clerk | 2024-03-10 | Email | Closed | 2024-02-20
AP22 |  | 046/24 | Confirm support to attempt to stop the closure of the Williton recycling centre | Clerk | 2024-02-19 | Email | Closed | 2024-02-16
AP23 |  | 047/24 | Submit response on AGAR complaints | Chair | 2024-02-29 | Email | Closed | 2024-02-19
AP24 |  | 042/24 | Confirm acceptance of quote for dog bin emptying (Somerset Council) | Clerk | 2024-03-10 | Email | Closed | 2024-02-20
AP25 |  | 060/24 | Order new chair for library | Clerk | 2024-04-10 | Email | Closed | 2024-03-26
AP26 |  | 057/24 | Confirm switch to Parish Online for the website and set up new email addresses | Clerk | 2024-04-10 | Email | Closed | 2024-03-24
AP27 |  | 052/24 | Return SID for a warranty repair | Clerk | 2024-04-10 | Collected | Closed | 2024-03-28
AP28 |  | 061/24 | Contact police to request a greater presence in the village | Clerk | 2024-04-10 | Email | Closed | 2024-03-20
AP29 |  | 052/24 | Ensure agendas for meetings are placed on notice boards in the parish | Cllr Orr | 2024-04-10 | Clerk and Cllr Orr now doing this | Closed | 2024-10-30
AP30 |  | 054/24 | Place risk assessment on the website | Clerk | When the new site is up and running |  | Closed | 2024-03-16
AP31 |  | 054/24 | Put flower boxes, library fittings and SID on the fixed asset register | Clerk | 2024-04-10 |  | Closed | 2024-03-28
AP32 |  | 059/24 | Ensure collection of rubbish from Station View | Cllr Rigby | 2024-04-10 |  | Closed | 2024-04-10
AP33 |  | 067/24 | Send support letter for railway link from Bishops Lydeard to Taunton | Cllr Martin | 2024-04-10 |  | Closed | 2024-06-10
AP34 |  | 068/24 | Contact lengthsman to establish time taken to complete certain tasks | Cllr Martin | 2024-04-10 |  | Closed | 2024-04-10
AP35 |  | 064/24 | Establish working party to develop an emergency plan for the village | Cllr Orr | Ongoing |  | Closed
AP36 |  | 069/24 | Obtain quotes to carry out repairs to Streamside path | Cllr Bletcher | 2024-04-10 | Bell Civil Engineering quotation accepted in mtg 13/11/2024 | Closed | 2024-11-30
AP37 |  | 068/24 | Prepare work schedule for the lengthsman | Cllr Hunt | TBA |  | Open
AP38 |  | 058/24 | Establish working party to oversee the roads project | Cllr Martin | 2024-04-10 |  | Closed | 2024-04-10
AP39 |  | 072/24 | Ensure full list of payments is circulated as part of the agenda for each meeting | Clerk | 2024-04-10 |  | Closed | 2024-04-10
AP40 |  | 084/24 | Contact Somerset Council re planning application comments from meeting on 10/4/24 | Clerk | 2024-05-08 | Email | Closed | 2024-04-18
AP41 |  | 086/24 | Arrange legal advice on school CIL application | Clerk | 2024-05-08 | Superceded by SALC advice | Closed | 2024-04-18
AP42 |  | 088/24 | Prepare Indemnity for Lengthsman VAT payment | Clerk | 2024-05-08 | Prepared but not required | Closed | 2024-10-09
AP43 |  | 089/24 | Discuss problem with storm drain on Taunton Road with DWH | Cllr Rigby | 2024-05-08 |  | Open
AP44 |  | 092/24 | Discuss option for Bleed Control Kits in the village | Cllr Allen | 2024-05-08 |  | Open
AP45 |  | 096/24 | Set up new email addresses for councillors | Clerk | 2024-05-08 |  | Closed | 2024-04-18
AP46 |  | 110/24 | Review subscription to Somerset Playing Fields Association | Clerk | 2024-06-10 | Email | Closed | 2024-05-21
AP47 |  | 111/24 | Review Standing Orders, Financial Regulations and Risk Assessment | Clerk | 2024-06-10 |  | Closed | 2024-06-12
AP48 |  | 118/24 | Village phone boxes policy | Clerk | 2024-06-10 |  | Closed | 2024-06-12
AP49 |  | 118/24 | Arrange further SID repair if required | Clerk | 2024-06-10 |  | Closed | 2024-05-15
AP50 |  | 121/24 | Bleed control kits consumables to be reviewed (092/24 above) | Clerk | 2024-06-10 | See 092/24 | Closed | 2024-05-15
AP51 |  | 124/24 | Obtain further information on proposed fish & chip van | Clerk | 2024-06-10 | Email | Closed | 2024-05-21
AP52 |  | 127/24 | Parish Lengthsman to attend the next PC meeting | Clerk | 2024-06-10 | Email | Closed | 2024-05-09
AP53 |  | 129/24 | Agree launch of new website | Clerk | 2024-06-10 |  | Closed | 2024-05-17
AP54 |  | 131/24 | Bus timetable near the underpass | Cllr Rigby | 2024-06-10 |  | Closed | 2024-05-17
AP55 |  | 133/24 | Clerk to obtain login details for the Parish Online mapping system | Clerk | 2024-06-10 |  | Closed | 2024-05-21
AP56 | June 2024 | 145/24 | Circulate blank financial regulations to councillors for completion at the next PC meeting | Clerk | 2024-07-10 |  | Closed | 2024-06-12
AP57 | June 2024 | 155/24 | Clarify verge cutting proposal with the lengthsman | Clerk | 2024-07-10 |  | Closed | 2024-06-27
AP58 | June 2024 | 157/24 | Renew insurance | Clerk | 2024-06-14 |  | Closed | 2024-06-14
AP59 | June 2024 | 163/24 | Update inspection rights for the website and noticeboards | Clerk | 2024-07-01 |  | Closed | 2024-06-14
AP60 | June 2024 | 163/24 | Update website for FOI regulations per ICO model publication scheme | Clerk | 2024-07-10 |  | Open
AP61 | July 2024 | 172/24 | Arrange for Station Green bin to be emptied | Cllr Rigby | 2024-08-14 |  | Closed | 2024-07-26
AP62 | July 2024 | 173/24 | Arrange for grit bins to be filled before the Winter | Clerk | 2024-09-30 | Request made Ref: 828306 | Closed | 2024-11-29
AP63 | July 2024 | 173/24 | Check adoption of roundabout on the A358 | Cllr Rigby | 2024-08-14 |  | Closed | 2024-07-25
AP64 | July 2024 | 173/24 | Ask Lengthsman to recharge the battery in the SID when necessary | Clerk | 2024-08-14 |  | Closed | 2024-07-25
AP65 | July 2024 | 180/24 | Contact Edventure re youth provision in the village | Cllr Hunt | 2024-08-14 | Proposal received and discussed in mtg 13/11/2024 | Closed
AP66 | July 2024 | 181/24 | Draft advert for a new cleaner for the toilets and place on the website | Clerk | 2024-08-14 |  | Closed | 2024-07-23
AP67 | July 2024 | 186/24 | Arrange for approval of the financial regulations at the August meeting | Clerk | 2024-08-14 |  | Closed | 2024-07-26
AP68 | August 2024 | 197/24 | Notify councillors of timetable for the election of a councillor | Clerk | 2024-08-17 |  | Closed | 2024-08-15
AP69 | August 2024 | 203/24 | Review work carried out by the Lengthsman | Cllrs Hunt & Bletcher | 2024-09-30 | Completed by Cllr Lewin-Harris and the clerk on 02/04/2025 | Closed | 2025-04-02
AP70 | August 2024 | 206/24 | Update from Cllr Rigby on Ash Priors Common | Cllr Rigby | 2024-09-11 |  | Open
AP71 | August 2024 | 210/24 | Put Ecological survey on the agenda for the September PC meeting | Clerk | 2024-09-05 |  | Closed | 2024-08-15
AP72 | August 2024 | 210/24 | Obtain quote for two speed indicator devices | Clerk | 2024-09-05 |  | Closed | 2024-08-15
AP73 | September 2024 | 236/24 | Recording of Parish Council meetings. | Clerk | 2024-11-13 |  | Closed | 2024-10-09
AP74 | October 2024 | 245/24 High Street/Church Street parking | Request red or yellow line to Somerset Council Highways | Clerk | 2024-11-13 | Request made - Ref: 828299. Refused. | Closed | 2024-12-05
AP75 | October 2024 | 246/24 Somerset Council Matters | Investigate and clarify scope of vegetation works at Ash Priors common. | Cllr Rigby | 2024-11-13 |  | Open
AP76 | October 2024 | 248/24 Comments from members of the public | Provide further information in response to the FOI request. | Cllr Lewin-Harris | 2024-11-13 | email sent | Closed | 2024-11-13
AP77 | October 2024 | 248/24 Comments from members of the public | Add Civility and Respect Pledge to next Parish Council agenda | Clerk | 2024-11-13 |  | Closed | 2024-11-13
AP78 | October 2024 | 248/24 Comments from members of the public | Check if poles provided for SIDs have been approved for use by Somerset Council | Clerk | 2024-11-13 | Raised planning department. No reply. As far as I can see no poles provided. | Closed | 2025-01-10
AP79 | October 2024 | 249/24 Planning Applications | Request and extension of planning application 06/24/0030. | Clerk | 2024-11-13 | email from Anthony Pick - I’ll make a note and on file a seek an Extension of Time from the applicant given we have just received additional information. | Closed | 2024-11-13
AP80 | October 2024 | 250/24 24 Consider and approve the indemnity for VAT payments | Raise the VAT claim and then pay Jack Councill when the funds are received. | Clerk | 2024-11-13 | VAT claim submitted Ref: KAKX-UYU3-AMO8 and paid | Closed | 2024-11-13
AP81 | October 2024 | 251/24 Lengthman’s Report | Weed Control - add this to the agenda for the next Parish Council meeting. | Clerk | 2024-11-13 | Now on agenda for January meeting | Closed | 2025-01-03
AP82 | October 2024 | 251/24 Lengthman’s Report | Confirm the underpass lighting situation and reported to Somerset Council as needed. | Clerk | 2024-11-13 | Visited underpass in the dark and confirmed all working | Closed | 2025-02-03
AP83 | October 2024 | 254/24 Approval of EDF Energy Framework | Investigate the applicability of the EDF framework agreement. | Clerk | 2024-11-13 | email sent 14/10/24 - relates to Library? CCS applies so we will use EDF | Closed | 2024-11-13
AP84 | October 2024 | 259/24 CIL update | Convene the next CIL Committee meeting | Cllr Lewin-Harris | 2024-11-13 | Meeting arranged for 29/10/2024 at 7pm | Closed | 2024-10-22
AP85 | October 2024 | 261/24 Consideration of quotes for the Streamside path resurfacing | Produce a requirement/ specification for the streamside path for contractors to quote against. | Cllr Bletcher | 2024-11-13 | Bell Civil Engineering quote accepted in mtg 13/11/2024 | Closed | 2024-11-13
AP86 | October 2024 | 262/24 Correspondence from members of the public | Prepare a draft correspondence policy for review. | Clerk | 2024-11-13 | No template fornd from NALC or SALC. Issue now closed. | Closed | 2024-12-14
AP87 | October 2024 | 268/24 Any Other Business | Add the cycleway between Bishops Lydeard and Taunton to next month’s agenda | Clerk | 2024-11-13 | See agenda 13/11/2024 | Closed | 2024-11-13
AP88 | CIL Mtg 29 October 2024 | C10/24 Public Question Time | The clerk to add the CIL Deadline issue to the next parish council meeting as an agenda item. | Clerk | 2024-11-13 | Completed | Closed | 2024-11-13
AP89 | CIL Mtg 29 October 2024 | C11/24 Revised application from Bishops Lydeard Football Club | Cllr Hunt agreed to investigate other funding opportunities for the Football club | Cllr Hunt | 2024-11-13 | Cllr Hunt sent the Football Club a link to a grant stream that may be of interest | Closed | 2024-12-11
AP90 | CIL Mtg 29 October 2024 | C13/24 Update on School Nursery Provision application | Clerk to go back to James Dakin and see if the project can be done in phases | Clerk | 2024-12-01 | Call made on 10/12/2024 - will review agian when DoE grant request result known. | Closed | 2024-12-10
AP91 | November 2024 | 276/24 Parish Council to consider a resolution to sign up to the civility and respect pledge | Cllr Bainbridge to send out further information on the Civility and Respect Pledge | Cllr Bainbridge | 2024-12-11 | email received on 04/12/2024 for circulation to councillors. | Closed | 2024-12-04
AP92 | November 2024 | 280/24a CIL Update | Clerk to check when the £50,000 CIL funding for Youth provision was committed | Clerk | 2024-12-11 | No specific Youth Provision budget. Each item is reviewed and approved. | Closed | 2024-12-14
AP93 | November 2024 | 280/24c CIL Update | Gary Brown to provide 3 quotes (with fencing and hedging separated) as requested | Gary Brown | 2024-12-11 | Called Gary on 10/12/2024 to remind him | Open
AP94 | November 2024 | 281/24 Streamside Path | Clerk to contact Bells Civil Engineering and confirm the quotation stands and agree start date and duration | Clerk | 2024-12-11 | Bell email confirms quotation - mtg arranged for 05/02/2025. | Closed | 2025-03-20
AP95 | November 2024 | 283/24 Clerks Report | Clerk to ensure the new SID are on the asset register and covered by the insurance certificate | Clerk | 2024-12-11 | Asset register updated. Email sent to Zurich Insurance. | Closed | 2024-12-10
AP96 | November 2024 | 284/24 Authorisation of the purchase of Edition 13 of the Arnold Baker Local Government Administration book | Clerk to order Edition 13 of the Arnold Baker Local Government Administration book | Clerk | 2024-12-11 | Checking SLCC membership to get a lower cost. Book ordered. | Closed | 2024-12-03
AP97 | November 2024 | 285/24 Authorisation to progress with purchase and implementation of Scribe Accounts | Clerk to contact Scribe and start the process to implement Scribe Accounts software. | Clerk | 2024-12-31 | Scribe software now available and being set up. | Closed | 2024-12-03
AP98 | November 2024 | 286/24 Library - blind quotation | Clerk to liaise with Wyvern blinds and request that the blinds are repaired | Clerk | 2024-12-11 | Blinds now repaired | Closed | 2024-12-10
AP99 | November 2024 | 287/24 Lengthman’s Report | Clerk to check the rules for SIDs in terms of approvals needed and how often they should be moved/ rotated | Clerk | 2024-12-11 | Online research started. Email sent to planning department. MOU with Somerset Council found. January PC Meeting agreed locations - Ref: 015/25. | Closed | 2025-01-08
AP100 | November 2024 | 287/24 Lengthman’s Report | Clerk to check if the issues noted by the Lengthman had been reported to Somerset Council. | Clerk | 2024-12-11 | Confirmed on 28/11/2024 | Closed | 2024-11-28
AP101 | November 2024 | 288/24 Grit bin proposal for Stairfoot | Clerk to order a new grit bin from B&Q | Clerk | 2024-12-11 | Ordered on 27/11/2024. Installed on 03/12/2024 | Closed | 2024-12-03
AP102 | November 2024 | 289/24 Avon & Somerset Police Report | Clerk to follow up with the Police Community Support Officer for an update on nails/ tacks on the road. | Clerk | 2024-12-11 | email from PCSO received and sent to councillors | Closed | 2024-11-20
AP103 | November 2024 | 295/24 British Gas Tariffs | Clerk to research electricity tariffs with a view to using a single provider for both the Library and Public Conveniences | Clerk | 2024-12-11 | Library subject to CCS agreement with EDF until 2027 | Closed | 2024-12-12
AP104 | November 2024 | 299/24 Any Other Business | Cllr Allen to confirm the practicality and costs of providing a hearing loop in the small hall. | Cllr Allen | 2024-12-11 | Clerk to follow up with David Smart | Open
AP105 | November 2024 | 299/24 Any Other Business | Add the community skip idea to the next agenda | Clerk | 2024-12-11 | Added | Closed | 2024-11-29
AP106 | December 2024 | 304/24 - Comments from members of the public | Contact Somerset Council and request that the grass at Wheatstones is cut. | Cllr Rigby | 2025-01-08 | email sent - quote received - Wheatstone Grass Cutting x16 cuts @ £93.62 per cut . Approved at Feb meeting ref 054/25 | Closed | 2025-02-12
AP107 | December 2024 | 305/24 Parish Path Liaison Officer (PPLO) proposal | Create a list of paths and volunteers | Mr Partington | 2025-01-08 | Reminder email sent | Open
AP108 | December 2024 | 306/24 Food Trailer proposal | Inform the owner of the agreement and restrictions | Clerk | 2025-01-08 | email sent and received with confirmation. | Closed | 2024-12-17
AP109 | December 2024 | 307/24 Community Skip proposal | Obtain quotations for the hire of a skip. | Clerk | 2025-01-08 | Quotes and paper prepared for meeting | Closed | 2025-01-03
AP110 | December 2024 | 308/24 Correspondence - War memorial Trust | Obtain 3 quotations for the work and apply for a grant. | Cllr Lewin-Harris | 2025-01-08 | 3 quotes received . Cllr Lewin-Harris to apply for a grant from the War memorial Trust - See Agenda Item 8 – 035/25. Grant applied for. | Closed | 2025-02-27
AP111 | December 2024 | 308/24 Correspondence - Parking restrictions over bridge | Request yellow lines are painted either side of the road over the bridge. | Clerk | 2025-01-08 | email sent to Traffic Management on 22/02/2025 and followed up. Response was - As part of our procedure we need to demonstrate evidence to the police before new parking restrictions can progressed to the next level. | Closed | 2025-04-06
AP112 | December 2024 | 308/24 - Power Outages following Storm Darragh | Contact Western Power and request action to be taken. | Clerk | 2025-01-08 | Complain raised (Ref:C010624/ 5399183). See national Grid email reply. | Closed | 2024-12-27
AP113 | December 2024 | 308/24 - Corespondence - Item 1 - Electricity outages over the weekend due to the storm. | Add the Emergency Plan to the next Parish Council meeting agenda | Clerk | 2025-01-08 | Added to genda | Closed | 2024-12-27
AP114 | December 2024 | 309/24 Planning Applications | Reply to the planning department in accordance to the PC instructions | Clerk | 2025-01-08 | email sent | Closed | 2024-12-17
AP115 | December 2024 | 311/24 Somerset Council Matters | The clerk to add the SRA grant to the next meeting agenda and Cllr Rigby to prepare in advance | Clerk & Cllr Rigby | 2025-01-08 | Added to Agenda. Cllr Rigby asked councillors to feedback ideas to the clerk. | Closed | 2025-02-12
AP116 | December 2024 | 313/24 Lengthman’s monthly report | Investigate if a spare pane of glass is available for the Mount Street/ Quantock View phone box | Lengthman | 2025-02-12 | The glass has been replaced. | Closed | 2025-02-12
AP117 | December 2024 | 316/24 Budget 2025/26 proposal | Amend the 2025/26 budget for final review at the next meeting. | Clerk | 2025-01-08 | Completed | Closed | 2025-01-03
AP118 | December 2024 | 319/24 EDF and British Gas Tariffs | Contact British Gas and arrange the new tariff. | Clerk | 2025-01-08 | email sent. Tariff now set up. | Closed | 2025-01-10
AP119 | December 2024 | 322/24 Any Other Business | Obtain quotations for a new notice board for Moorland Gate and one to replace the existing one opposite the primary school. | Clerk | 2025-02-12 | See Paper for PC Meeting on 12th February 2025 | Closed | 2025-02-12
AP120 | December 2024 | 322/24 Any Other Business | Talk to David Smart about getting the St Mary's Church wall repaired. | Clerk | 2025-01-08 | Clerk to write a letter to the owner of the COOP building who is responsible. | Open

## 2025 Actions
Bishops Lydeard & Cothelstone Parish Council Action Tracker
Action Point | PC Meeting | Meeting Minutes Reference | Action | Responsibility | Target Completion Date | Comments | Status | Date Completed
AP121 | January 2025 | 005/25 - Comments from members of the public | Cllr Rigby to provide an update on the speed limit review on the A358 instigated by Somerset Council in 2023 as soon as possible. | Cllr Rigby | 2025-01-31 |  | Open
AP122 | January 2025 | 005/25 - Comments from members of the public | The clerk to add a review of the members of the working groups and committees at the next Parish Council meeting. | Clerk | 2025-02-06 | Deferred to the annual meeting in May | Closed | 2025-05-09
AP123 | January 2025 | 012/25 - Community Skip Hire Costs | More information is required, and the Clerk is to research skip hire further and bring back to the council for approval. | Clerk | 2025-03-31 |  | Open
AP124 | January 2025 | 014/25 - Weed control proposals | Clerk to research weed killer policies and practices used in other organisations. | Clerk | 2025-02-28 | On the agenda for 12th April 2025 | Open
AP125 | January 2025 | 020/25 - Budget 2025/26 and Precept | The clerk to complete the 2025/26 Precept form and return it to Somerset Council before the end of January 2025. | Clerk | 2025-01-31 | Form returned and acknowledged | Closed | 2025-01-10
AP126 | January 2025 | 024/25 - Poppy of Honour War Memorial Appeal | Cllr Lewin-Harris to order the Poppy of Honour War Memorial plaque via the link provided. | Cllr Lewin-Harris | 2025-03-31 | Completed and email received | Closed | 2025-03-17
AP127 | January 2025 | 027/25 - Any Other Business | The clerk to arrange an emergency Parish Council meeting regarding the Road & Traffic project following feedback from Somerset Council to the brief provided on 24th December 2024. | Clerk | 2025-02-06 | The feedback will be provided at the Parish Council meeting on 12th Februray 2025 | Closed | 2025-02-05
AP128 | January 2025 | 027/25 - Any Other Business | The clerk is to ask the Somerset Council planning team if planning application Ref: 53/24/0006 has been amended | Clerk | 2025-02-06 | Checked planning application - found 53/24/0007 and emailed Councillors | Closed | 2025-02-05
AP129 | January 2025 | 027/25 - Any Other Business | The clerk is to investigate who in Somerset Council we need to contact regarding leasing the woodland between Minehead Road and the A358 bypass. | Clerk | 2025-03-31 | email sent to Charlie Field, Strategic Manager Estates, Somerset Council. Then to devolution email address | Closed | 2025-05-09
AP130 | February 2025 | 032/25 - Comments from members of the public | The clerk to contact the PCSO and ask if she can visit the location (streamside path) a few times a week | Clerk | 2025-03-31 | Completed and acknolwedged | Closed | 2025-03-09
AP131 | February 2025 | 034/25 - Civility and Respect | Clerk to complete an audit the Parish Council policies and procedures and identify gaps with the Civility and Respect requirements | Clerk | 2025-03-31 |  | Open
AP132 | February 2025 | 036/25 - Bishops Lydeard Leaflet | Cllr Lewin-Harris to confirm estimated costs of leaflet changes with the supplier. | Cllr Lewin-Harris | 2025-03-06 |  | Open
AP133 | February 2025 | 040/25 - Skate Park Trial Location Update | The clerk to research the potential costs (lease/ purchase cost, legal fees, maintenance fees etc.) of the Play Area by the station. | Clerk | 2025-03-31 | email sent to Julian Grant - then devolution team | Open
AP134 | February 2025 | 041/25 - Digital Café Update | The clerk is to contact the people running the coffee mornings (Talking Café) in the Village Hall to find out more. | Clerk | 2025-03-06 | Meeting arranged for Thursday 5th March 2025. | Closed | 2025-03-05
AP135 | February 2025 | 042/25 - Greenway Woodland | The clerk to provide information relating to the sale of the woodland (condition of the woodland, seller’s timescales and expected price, costs, etc.) | Clerk | 2025-03-31 | Meeting arranged for 3rd March 2025. Discussed at PC Meeting on 12th March. Costs etc. needed. Costs ready for mtg on 09/05/2025 | Closed | 2025-05-14
AP135 | February 2025 | 043/25 - Approval to purchase new Noticeboards | Clerk to obtain alternative quotes for the noticeboards at Moorland Gate and opposite the school. | Clerk | 2025-03-06 | On the agenda for 12th April 2025 and 9th May 2025. Now on order. | Closed | 2025-05-30
AP135 | February 2025 | 043/25 - Approval to purchase new Noticeboards | Clerk to purchase the noticeboard for the Quantock View phone box. | Clerk | 2025-03-31 | On the agenda for 12th April 2025 and 9th May 2025. Now on order. | Closed | 2025-05-30
AP136 | March 2025 | 063/25 Opening/ Closing Public Toilets | The clerk to enquire whether Fairy Dust Cleaning and Care Services would be willing to close the Public Toilets on Saturday, open and close them on Sundays and Bank Holidays (with the exception on Christmas Day and Boxing Day), clean the toilets on the additional days and if so at what cost. | Clerk | 2025-03-31 | email sent. Quote ready for next Parish Council meeting | Closed | 2025-03-31
AP137 | March 2025 | 066/25 Digital Café location | The clerk is to coordinate with the Digital Café representative and organise the meetings with the Talking Café Village Agent. | Clerk | 2025-03-31 | Planning to start on Thursday 3rd April 2025 | Closed | 2025-03-31
AP138 | March 2025 | 068/25 Asset Register | Clerk to add £1 minimum value, current value to the asset register, and restate last years AGAR Box | Clerk | 2025-03-31 | Completed | Closed | 2025-03-31
AP139 | March 2025 | 069/25 Risk Register review | The clerk to prepare a separate MUGA Risk Assessment document | Clerk | 2025-04-30 |  | Open
AP140 | March 2025 | 072/25 Finance | The clerk is to check the scope of work in the contract for the lengthsman. | Clerk | 2025-03-31 | Meeting held - document to be updated | Open
AP141 | March 2025 | 084/25 Any Other Business | Clerk to request that Somerset Council maintain the bank that backs onto Kings Yard and Webbers on Mill Lane. | Clerk | 2025-04-30 | Raised with Somerset Council - Report reference: 841538 | Closed | 2025-04-11
AP142 | March 2025 | 084/25 Any Other Business | The Chair and the Clerk will propose possible dates and venues for the Annual Parish Meeting and the Annual Meeting of the Council for agreement. | Chair & Clerk | 2025-03-31 | Annual Parish Meeting planned for 21st May. The Annual Meeting of the Council for 14th May | Closed | 2025-03-31
AP143 | April 2025 | 090/25 Opening/ Closing Public Toilets | The clerk to investigate alternative automated locking mechanisms for the toilet doors. | Clerk | 2025-05-31 |  | Open
AP144 | April 2025 | 91/25 Approval to purchase new toilet roll holders for the Public Conveniences | The clerk to purchase two ETAL Lockable Double Toilet Roll Holder in Stainless Steel at £39.99 each. | Clerk | 2025-05-14 | Completed | Open | 2025-05-09
AP145 | April 2025 | 095/25 Authorisation of HSBC Bank Mandate to add Clerk/ RFO as a Signatory | Cllr Lewin-Harris to setup online banking with HSBC. The Clerk to be setup as administrator for the account | Cllr Lewin-Harris | 2025-05-31 | Forms rejected by HSBC and the clerk is not on Mandate | Open
AP146 | April 2025 | 097/25 Correspondence | Clerk to raise the issue of the caravan parked on Taunton Road with the police. | Clerk | 2025-04-28 | Reported to PCSO via email on 14/04/2025. Response was no action can be taken. | Closed | 2025-04-15
AP147 | April 2025 | 098/25 Draft Emergency Plan | Cllr Roberts to bring more information to the next meeting | Cllr Roberts | 2025-05-07 | Delayed to July meeting | Open
AP148 | May 2025 | 119/25 and 120/25 Review of documents and policies | The clerk is to amend section 16.5 of the Finance Regulations and update all the documents with the ‘adopted date’ and ‘next review date’. | Clerk | 2025-05-31 |  | Open
AP149 | May 2025 | 123/25 Decision to Purchase Noticeboards | The clerk is to progress the noticeboard orders for signs with Arien Signs Ltd. | Clerk | 2025-05-31 | Signs now on order | Closed | 2025-06-02
AP150 | May 2025 | 126/25 Decision to Approve additional solar panels and brackets for the two SIDS | The clerk is to progress the order for two additional solar panels and brackets | Clerk | 2025-05-31 | Contcated Huga Barr to arrange deleivery. Now delivered. | Closed | 2025-05-30
AP151 | May 2025 | 126/25 Decision to Approve additional solar panels and brackets for the two SIDS | The clerk is to investigate if it is possible to collect speed data from the Speed Indicator Devices. | Clerk | 2025-06-11 | Discussed with Lengthman on 19/05/2025. Need to download software and try it out. | Open
AP152 | May 2025 | 127/25 New Lights for the Public Conveniences | The clerk is to obtain additional quotations for replacement lights in the Public Conveniences. | Clerk | 2025-06-11 |  | Open
AP153 | May 2025 | 129/25 CIL Update | The clerk to express an interest in the Community Hall in Darby Way and request more information on the open space land at Hither Mead. | Clerk | 2025-06-11 | Email sent about Darby Way and email received confirming open space land which is on the agnda for the June meeting. | Closed | 2025-05-30
AP154 | May 2025 | 129/25 CIL Update | The clerk is to send the link to the Somerset Council list of assets to the councillors. | Clerk | 2025-05-19 | email sent on 16/05/2025 | Closed | 2025-05-16
AP155 | May 2025 | 133/25 Finance | The clerk to amend the Regular Payments paper and look into stopping the gmail email account. | Clerk | 2025-06-11 | Regular Payments paper updated on 16/05/2025 | Open
AP156 | May 2025 | 141/25 AOB | The clerk to contact the farmer and arrange an onsite meeting regarding Whiskey Trail. | Clerk | 2025-06-11 |  | Open
AP157 | May 2025 | 141/25 AOB | The clerk to contact the lengthsman and request that the footpath is mowed which usually takes place in May and October. | Clerk | 2025-05-31 | Phonecall made on 19/05/2025 | Closed | 2025-05-19