## 2024 Actions
Bishops Lydeard & Cothelstone Parish Council Action Tracker
Action Point | PC Meeting | Meeting Minutes Reference | Action | Responsibility | Target Completion Date | Comments | Status | Date Completed
AP1 |  | 005/24 | Contact SALC re councillors email addresses and domain name | Clerk | 2024-01-31 |  | Closed | 2024-01-15
AP2 |  | 007/24a | Arrange for grit bins to be filled and one bin replaced | Clerk | 2024-01-31 | SC Council contacted | Closed | 2024-01-15
AP3 |  | 007/24b | Arrange for rubbish collection from the carpark | Clerk | 2024-01-31 | SC Council contacted | Closed | 2024-01-19
Ref SWT578828520
AP4 |  | 007/24c | Drains to be cleaned on A358 to prevent possible flooding | Clerk | 2024-01-31 | SC Council contacted | Closed | 2024-01-19
Ref 698225
AP5 |  | 007/24d | Whiskey Trail footpath to be filled with stone | Clerk | 2024-01-31 | On agenda 14/2/24 | Closed | 2024-02-02
AP6 |  | 008/24 | Planning 06/23/0036 Support but with expression of concern over car parking | Clerk | 2024-01-19 |  | Closed | 2024-01-16
AP7 |  | 009/24 | Quantock Vale surgery to dispense drugs - support the application | Clerk | 2024-01-19 |  | Closed | 2024-01-16
AP8 |  | 010/24 | Contact PCSO for more information on police report | Clerk | 2024-01-19 | Not possible due to GDPR | Closed | 2024-01-31
AP9 |  | 011/24 | Arrange for Somerset Gazette to be ordered for the library | Clerk | 2024-01-19 |  | Closed | 2024-01-15
AP10 |  | 012/24 | Response to AGAR queries | Chair/Clerk | 2024-02-13 |  | Closed | 2024-02-05
AP11 |  | 044/24 | Defribrillator for school (£500) - agenda for meeting 14/2/24 | Clerk | 2024-02-10 |  | Closed | 2024-01-15
AP12 |  | 043/24 | Carpet cleaning Library (£100 quote awaited) - agenda 14/2/24 | Clerk | 2024-02-05 |  | Closed | 2024-02-13
AP13 |  | 026/24 | Website and email addresses proposal | Clerk | 2024-03-10 |  | Closed | 2024-02-27
AP14 |  | 032/24 | Proposal for scoping exercise on youth provision in the village | P Durban | 2024-04-10 | Closed | Closed | N/A
AP15 |  | 032/24 | Establish Working Party on flood risk and prevention | Cllr Orr | 2024-04-10 | Deferred to 11/12/2024 | Closed
AP16 |  | 037/24 | Reports on road and traffic issues to be submitted to Somerset Council | Chair | 2024-03-10 |  | Closed | 2024-02-19
AP17 |  | 037/24 | Report on CIL funds and fixed assets | Clerk | 2024-03-10 |  | Closed | 2024-02-26
AP18 |  | 037/24 | Report on possible acquisition of Ash Priors Common | Cllr Rigby | 2024-03-10 | See AP70 | Closed
AP19 |  | 045/24 | Follow up on fly tipping on Broadgate | Clerk | 2024-03-10 | Email | Closed | 2024-02-20
AP20 |  | 045/24 | Query time taken to clear rubbish in the underpass | Clerk | 2024-03-10 | Email | Closed | 2024-02-20
AP21 |  | 045/24 | Ask Lengthsman to stain the notice board on Greenway | Clerk | 2024-03-10 | Email | Closed | 2024-02-20
AP22 |  | 046/24 | Confirm support to attempt to stop the closure of the Williton recycling centre | Clerk | 2024-02-19 | Email | Closed | 2024-02-16
AP23 |  | 047/24 | Submit response on AGAR complaints | Chair | 2024-02-29 | Email | Closed | 2024-02-19
AP24 |  | 042/24 | Confirm acceptance of quote for dog bin emptying (Somerset Council) | Clerk | 2024-03-10 | Email | Closed | 2024-02-20
AP25 |  | 060/24 | Order new chair for library | Clerk | 2024-04-10 | Email | Closed | 2024-03-26
AP26 |  | 057/24 | Confirm switch to Parish Online for the website and set up new email addresses | Clerk | 2024-04-10 | Email | Closed | 2024-03-24
AP27 |  | 052/24 | Return SID for a warranty repair | Clerk | 2024-04-10 | Collected | Closed | 2024-03-28
AP28 |  | 061/24 | Contact police to request a greater presence in the village | Clerk | 2024-04-10 | Email | Closed | 2024-03-20
AP29 |  | 052/24 | Ensure agendas for meetings are placed on notice boards in the parish | Cllr Orr | 2024-04-10 | Clerk and Cllr Orr now doing this | Closed | 2024-10-30
AP30 |  | 054/24 | Place risk assessment on the website | Clerk | When the new site is up and running |  | Closed | 2024-03-16
AP31 |  | 054/24 | Put flower boxes, library fittings and SID on the fixed asset register | Clerk | 2024-04-10 |  | Closed | 2024-03-28
AP32 |  | 059/24 | Ensure collection of rubbish from Station View | Cllr Rigby | 2024-04-10 |  | Closed | 2024-04-10
AP33 |  | 067/24 | Send support letter for railway link from Bishops Lydeard to Taunton | Cllr Martin | 2024-04-10 |  | Closed | 2024-06-10
AP34 |  | 068/24 | Contact lengthsman to establish time taken to complete certain tasks | Cllr Martin | 2024-04-10 |  | Closed | 2024-04-10
AP35 |  | 064/24 | Establish working party to develop an emergency plan for the village | Cllr Orr | 2024-04-10 | Now Cllr Roberts and P Durban | Closed | 2025-04-09
AP36 |  | 069/24 | Obtain quotes to carry out repairs to Streamside path | Cllr Bletcher | 2024-04-10 | Bell Civil Engineering quotation accepted in mtg 13/11/2024 | Closed | 2024-11-30
AP37 |  | 068/24 | Prepare work schedule for the lengthsman | Cllr Hunt | TBA | Closed - see AP140 (2025 action) | Closed | 2025-03-14
AP38 |  | 058/24 | Establish working party to oversee the roads project | Cllr Martin | 2024-04-10 |  | Closed | 2024-04-10
AP39 |  | 072/24 | Ensure full list of payments is circulated as part of the agenda for each meeting | Clerk | 2024-04-10 |  | Closed | 2024-04-10
AP40 |  | 084/24 | Contact Somerset Council re planning application comments from meeting on 10/4/24 | Clerk | 2024-05-08 | Email | Closed | 2024-04-18
AP41 |  | 086/24 | Arrange legal advice on school CIL application | Clerk | 2024-05-08 | Superceded by SALC advice | Closed | 2024-04-18
AP42 |  | 088/24 | Prepare Indemnity for Lengthsman VAT payment | Clerk | 2024-05-08 | Prepared but not required | Closed | 2024-10-09
AP43 |  | 089/24 | Discuss problem with storm drain on Taunton Road with DWH | Cllr Rigby | 2024-05-08 | Closed | Closed | N/A
AP44 |  | 092/24 | Discuss option for Bleed Control Kits in the village | Cllr Allen | 2024-05-08 | Bleed kit now available at the village hall. | Closed | 2024-12-31
AP45 |  | 096/24 | Set up new email addresses for councillors | Clerk | 2024-05-08 |  | Closed | 2024-04-18
AP46 |  | 110/24 | Review subscription to Somerset Playing Fields Association | Clerk | 2024-06-10 | Email | Closed | 2024-05-21
AP47 |  | 111/24 | Review Standing Orders, Financial Regulations and Risk Assessment | Clerk | 2024-06-10 |  | Closed | 2024-06-12
AP48 |  | 118/24 | Village phone boxes policy | Clerk | 2024-06-10 |  | Closed | 2024-06-12
AP49 |  | 118/24 | Arrange further SID repair if required | Clerk | 2024-06-10 |  | Closed | 2024-05-15
AP50 |  | 121/24 | Bleed control kits consumables to be reviewed (092/24 above) | Clerk | 2024-06-10 | See 092/24 | Closed | 2024-05-15
AP51 |  | 124/24 | Obtain further information on proposed fish & chip van | Clerk | 2024-06-10 | Email | Closed | 2024-05-21
AP52 |  | 127/24 | Parish Lengthsman to attend the next PC meeting | Clerk | 2024-06-10 | Email | Closed | 2024-05-09
AP53 |  | 129/24 | Agree launch of new website | Clerk | 2024-06-10 |  | Closed | 2024-05-17
AP54 |  | 131/24 | Bus timetable near the underpass | Cllr Rigby | 2024-06-10 |  | Closed | 2024-05-17
AP55 |  | 133/24 | Clerk to obtain login details for the Parish Online mapping system | Clerk | 2024-06-10 |  | Closed | 2024-05-21
AP56 | June 2024 | 145/24 | Circulate blank financial regulations to councillors for completion at the next PC meeting | Clerk | 2024-07-10 |  | Closed | 2024-06-12
AP57 | June 2024 | 155/24 | Clarify verge cutting proposal with the lengthsman | Clerk | 2024-07-10 |  | Closed | 2024-06-27
AP58 | June 2024 | 157/24 | Renew insurance | Clerk | 2024-06-14 |  | Closed | 2024-06-14
AP59 | June 2024 | 163/24 | Update inspection rights for the website and noticeboards | Clerk | 2024-07-01 |  | Closed | 2024-06-14
AP60 | June 2024 | 163/24 | Update website for FOI regulations per ICO model publication scheme | Clerk | 2024-07-10 | Publication scheme 2025/26 prepared and uploaded to website | Closed | 2025-09-02
AP61 | July 2024 | 172/24 | Arrange for Station Green bin to be emptied | Cllr Rigby | 2024-08-14 |  | Closed | 2024-07-26
AP62 | July 2024 | 173/24 | Arrange for grit bins to be filled before the Winter | Clerk | 2024-09-30 | Request made Ref: 828306 | Closed | 2024-11-29
AP63 | July 2024 | 173/24 | Check adoption of roundabout on the A358 | Cllr Rigby | 2024-08-14 |  | Closed | 2024-07-25
AP64 | July 2024 | 173/24 | Ask Lengthsman to recharge the battery in the SID when necessary | Clerk | 2024-08-14 |  | Closed | 2024-07-25
AP65 | July 2024 | 180/24 | Contact Edventure re youth provision in the village | Cllr Hunt | 2024-08-14 | Proposal received and discussed in mtg 13/11/2024 | Closed
AP66 | July 2024 | 181/24 | Draft advert for a new cleaner for the toilets and place on the website | Clerk | 2024-08-14 |  | Closed | 2024-07-23
AP67 | July 2024 | 186/24 | Arrange for approval of the financial regulations at the August meeting | Clerk | 2024-08-14 |  | Closed | 2024-07-26
AP68 | August 2024 | 197/24 | Notify councillors of timetable for the election of a councillor | Clerk | 2024-08-17 |  | Closed | 2024-08-15
AP69 | August 2024 | 203/24 | Review work carried out by the Lengthsman | Cllrs Hunt & Bletcher | 2024-09-30 | Completed by Cllr Lewin-Harris and the clerk on 02/04/2025 | Closed | 2025-04-02
AP70 | August 2024 | 206/24 | Update from Cllr Rigby on Ash Priors Common | Cllr Rigby | 2024-09-11 | Closed | Closed | N/A
AP71 | August 2024 | 210/24 | Put Ecological survey on the agenda for the September PC meeting | Clerk | 2024-09-05 |  | Closed | 2024-08-15
AP72 | August 2024 | 210/24 | Obtain quote for two speed indicator devices | Clerk | 2024-09-05 |  | Closed | 2024-08-15
AP73 | September 2024 | 236/24 | Recording of Parish Council meetings. | Clerk | 2024-11-13 |  | Closed | 2024-10-09
AP74 | October 2024 | 245/24 High Street/Church Street parking | Request red or yellow line to Somerset Council Highways | Clerk | 2024-11-13 | Request made - Ref: 828299. Refused. | Closed | 2024-12-05
AP75 | October 2024 | 246/24 Somerset Council Matters | Investigate and clarify scope of vegetation works at Ash Priors common. | Cllr Rigby | 2024-11-13 | Closed | Closed | N/A
AP76 | October 2024 | 248/24 Comments from members of the public | Provide further information in response to the FOI request. | Cllr Lewin-Harris | 2024-11-13 | email sent | Closed | 2024-11-13
AP77 | October 2024 | 248/24 Comments from members of the public | Add Civility and Respect Pledge to next Parish Council agenda | Clerk | 2024-11-13 |  | Closed | 2024-11-13
AP78 | October 2024 | 248/24 Comments from members of the public | Check if poles provided for SIDs have been approved for use by Somerset Council | Clerk | 2024-11-13 | Raised planning department. No reply. As far as I can see no poles provided. | Closed | 2025-01-10
AP79 | October 2024 | 249/24 Planning Applications | Request and extension of planning application 06/24/0030. | Clerk | 2024-11-13 | email from Anthony Pick - I’ll make a note and on file a seek an Extension of Time from the applicant given we have just received additional information. | Closed | 2024-11-13
AP80 | October 2024 | 250/24 24 Consider and approve the indemnity for VAT payments | Raise the VAT claim and then pay Jack Councill when the funds are received. | Clerk | 2024-11-13 | VAT claim submitted Ref: KAKX-UYU3-AMO8 and paid | Closed | 2024-11-13
AP81 | October 2024 | 251/24 Lengthman’s Report | Weed Control - add this to the agenda for the next Parish Council meeting. | Clerk | 2024-11-13 | Now on agenda for January meeting | Closed | 2025-01-03
AP82 | October 2024 | 251/24 Lengthman’s Report | Confirm the underpass lighting situation and reported to Somerset Council as needed. | Clerk | 2024-11-13 | Visited underpass in the dark and confirmed all working | Closed | 2025-02-03
AP83 | October 2024 | 254/24 Approval of EDF Energy Framework | Investigate the applicability of the EDF framework agreement. | Clerk | 2024-11-13 | email sent 14/10/24 - relates to Library? CCS applies so we will use EDF | Closed | 2024-11-13
AP84 | October 2024 | 259/24 CIL update | Convene the next CIL Committee meeting | Cllr Lewin-Harris | 2024-11-13 | Meeting arranged for 29/10/2024 at 7pm | Closed | 2024-10-22
AP85 | October 2024 | 261/24 Consideration of quotes for the Streamside path resurfacing | Produce a requirement/ specification for the streamside path for contractors to quote against. | Cllr Bletcher | 2024-11-13 | Bell Civil Engineering quote accepted in mtg 13/11/2024 | Closed | 2024-11-13
AP86 | October 2024 | 262/24 Correspondence from members of the public | Prepare a draft correspondence policy for review. | Clerk | 2024-11-13 | No template fornd from NALC or SALC. Issue now closed. | Closed | 2024-12-14
AP87 | October 2024 | 268/24 Any Other Business | Add the cycleway between Bishops Lydeard and Taunton to next month’s agenda | Clerk | 2024-11-13 | See agenda 13/11/2024 | Closed | 2024-11-13
AP88 | CIL Mtg 29 October 2024 | C10/24 Public Question Time | The clerk to add the CIL Deadline issue to the next parish council meeting as an agenda item. | Clerk | 2024-11-13 | Completed | Closed | 2024-11-13
AP89 | CIL Mtg 29 October 2024 | C11/24 Revised application from Bishops Lydeard Football Club | Cllr Hunt agreed to investigate other funding opportunities for the Football club | Cllr Hunt | 2024-11-13 | Cllr Hunt sent the Football Club a link to a grant stream that may be of interest | Closed | 2024-12-11
AP90 | CIL Mtg 29 October 2024 | C13/24 Update on School Nursery Provision application | Clerk to go back to James Dakin and see if the project can be done in phases | Clerk | 2024-12-01 | Call made on 10/12/2024 - will review agian when DoE grant request result known. | Closed | 2024-12-10
AP91 | November 2024 | 276/24 Parish Council to consider a resolution to sign up to the civility and respect pledge | Cllr Bainbridge to send out further information on the Civility and Respect Pledge | Cllr Bainbridge | 2024-12-11 | email received on 04/12/2024 for circulation to councillors. | Closed | 2024-12-04
AP92 | November 2024 | 280/24a CIL Update | Clerk to check when the £50,000 CIL funding for Youth provision was committed | Clerk | 2024-12-11 | No specific Youth Provision budget. Each item is reviewed and approved. | Closed | 2024-12-14
AP93 | November 2024 | 280/24c CIL Update | Gary Brown to provide 3 quotes (with fencing and hedging separated) as requested | Gary Brown | 2024-12-11 | Called Gary on 10/12/2024 to remind him. Agreed to close this CIL application during the November 2025 meeting. | Closed | 2025-11-12
AP94 | November 2024 | 281/24 Streamside Path | Clerk to contact Bells Civil Engineering and confirm the quotation stands and agree start date and duration | Clerk | 2024-12-11 | Bell email confirms quotation - mtg arranged for 05/02/2025. | Closed | 2025-03-20
AP95 | November 2024 | 283/24 Clerks Report | Clerk to ensure the new SID are on the asset register and covered by the insurance certificate | Clerk | 2024-12-11 | Asset register updated. Email sent to Zurich Insurance. | Closed | 2024-12-10
AP96 | November 2024 | 284/24 Authorisation of the purchase of Edition 13 of the Arnold Baker Local Government Administration book | Clerk to order Edition 13 of the Arnold Baker Local Government Administration book | Clerk | 2024-12-11 | Checking SLCC membership to get a lower cost. Book ordered. | Closed | 2024-12-03
AP97 | November 2024 | 285/24 Authorisation to progress with purchase and implementation of Scribe Accounts | Clerk to contact Scribe and start the process to implement Scribe Accounts software. | Clerk | 2024-12-31 | Scribe software now available and being set up. | Closed | 2024-12-03
AP98 | November 2024 | 286/24 Library - blind quotation | Clerk to liaise with Wyvern blinds and request that the blinds are repaired | Clerk | 2024-12-11 | Blinds now repaired | Closed | 2024-12-10
AP99 | November 2024 | 287/24 Lengthman’s Report | Clerk to check the rules for SIDs in terms of approvals needed and how often they should be moved/ rotated | Clerk | 2024-12-11 | Online research started. Email sent to planning department. MOU with Somerset Council found. January PC Meeting agreed locations - Ref: 015/25. | Closed | 2025-01-08
AP100 | November 2024 | 287/24 Lengthman’s Report | Clerk to check if the issues noted by the Lengthman had been reported to Somerset Council. | Clerk | 2024-12-11 | Confirmed on 28/11/2024 | Closed | 2024-11-28
AP101 | November 2024 | 288/24 Grit bin proposal for Stairfoot | Clerk to order a new grit bin from B&Q | Clerk | 2024-12-11 | Ordered on 27/11/2024. Installed on 03/12/2024 | Closed | 2024-12-03
AP102 | November 2024 | 289/24 Avon & Somerset Police Report | Clerk to follow up with the Police Community Support Officer for an update on nails/ tacks on the road. | Clerk | 2024-12-11 | email from PCSO received and sent to councillors | Closed | 2024-11-20
AP103 | November 2024 | 295/24 British Gas Tariffs | Clerk to research electricity tariffs with a view to using a single provider for both the Library and Public Conveniences | Clerk | 2024-12-11 | Library subject to CCS agreement with EDF until 2027 | Closed | 2024-12-12
AP104 | November 2024 | 299/24 Any Other Business | Cllr Allen to confirm the practicality and costs of providing a hearing loop in the small hall. | Cllr Allen | 2024-12-11 | Clerk to follow up with David Smart - See AP178 | Closed | 2025-10-31
AP105 | November 2024 | 299/24 Any Other Business | Add the community skip idea to the next agenda | Clerk | 2024-12-11 | Added | Closed | 2024-11-29
AP106 | December 2024 | 304/24 - Comments from members of the public | Contact Somerset Council and request that the grass at Wheatstones is cut. | Cllr Rigby | 2025-01-08 | email sent - quote received - Wheatstone Grass Cutting x16 cuts @ £93.62 per cut . Approved at Feb meeting ref 054/25 | Closed | 2025-02-12
AP107 | December 2024 | 305/24 Parish Path Liaison Officer (PPLO) proposal | Create a list of paths and volunteers | Mr Partington | 2025-01-08 | Reminder email sent | Open
AP108 | December 2024 | 306/24 Food Trailer proposal | Inform the owner of the agreement and restrictions | Clerk | 2025-01-08 | email sent and received with confirmation. | Closed | 2024-12-17
AP109 | December 2024 | 307/24 Community Skip proposal | Obtain quotations for the hire of a skip. | Clerk | 2025-01-08 | Quotes and paper prepared for meeting | Closed | 2025-01-03
AP110 | December 2024 | 308/24 Correspondence - War memorial Trust | Obtain 3 quotations for the work and apply for a grant. | Cllr Lewin-Harris | 2025-01-08 | 3 quotes received . Cllr Lewin-Harris to apply for a grant from the War memorial Trust - See Agenda Item 8 – 035/25. Grant applied for. | Closed | 2025-02-27
AP111 | December 2024 | 308/24 Correspondence - Parking restrictions over bridge | Request yellow lines are painted either side of the road over the bridge. | Clerk | 2025-01-08 | email sent to Traffic Management on 22/02/2025 and followed up. Response was - As part of our procedure we need to demonstrate evidence to the police before new parking restrictions can progressed to the next level. | Closed | 2025-04-06
AP112 | December 2024 | 308/24 - Power Outages following Storm Darragh | Contact Western Power and request action to be taken. | Clerk | 2025-01-08 | Complain raised (Ref:C010624/ 5399183). See national Grid email reply. | Closed | 2024-12-27
AP113 | December 2024 | 308/24 - Corespondence - Item 1 - Electricity outages over the weekend due to the storm. | Add the Emergency Plan to the next Parish Council meeting agenda | Clerk | 2025-01-08 | Added to genda | Closed | 2024-12-27
AP114 | December 2024 | 309/24 Planning Applications | Reply to the planning department in accordance to the PC instructions | Clerk | 2025-01-08 | email sent | Closed | 2024-12-17
AP115 | December 2024 | 311/24 Somerset Council Matters | The clerk to add the SRA grant to the next meeting agenda and Cllr Rigby to prepare in advance | Clerk & Cllr Rigby | 2025-01-08 | Added to Agenda. Cllr Rigby asked councillors to feedback ideas to the clerk. | Closed | 2025-02-12
AP116 | December 2024 | 313/24 Lengthman’s monthly report | Investigate if a spare pane of glass is available for the Mount Street/ Quantock View phone box | Lengthman | 2025-02-12 | The glass has been replaced. | Closed | 2025-02-12
AP117 | December 2024 | 316/24 Budget 2025/26 proposal | Amend the 2025/26 budget for final review at the next meeting. | Clerk | 2025-01-08 | Completed | Closed | 2025-01-03
AP118 | December 2024 | 319/24 EDF and British Gas Tariffs | Contact British Gas and arrange the new tariff. | Clerk | 2025-01-08 | email sent. Tariff now set up. | Closed | 2025-01-10
AP119 | December 2024 | 322/24 Any Other Business | Obtain quotations for a new notice board for Moorland Gate and one to replace the existing one opposite the primary school. | Clerk | 2025-02-12 | See Paper for PC Meeting on 12th February 2025 | Closed | 2025-02-12
AP120 | December 2024 | 322/24 Any Other Business | Talk to David Smart about getting the St Mary's Church wall repaired. | Clerk | 2025-01-08 | Clerk to write a letter to the owner of the COOP building who is responsible. | Closed | 2025-05-06

## 2025 Actions
Bishops Lydeard & Cothelstone Parish Council Action Tracker
Action Point | PC Meeting | Meeting Minutes Reference | Action | Responsibility | Target Completion Date | Comments | Status | Date Completed
AP121 | January 2025 | 005/25 - Comments from members of the public | Cllr Rigby to provide an update on the speed limit review on the A358 instigated by Somerset Council in 2023 as soon as possible. | Cllr Rigby | 2025-01-31 |  | Open
AP125 | January 2025 | 020/25 - Budget 2025/26 and Precept | The clerk to complete the 2025/26 Precept form and return it to Somerset Council before the end of January 2025. | Clerk | 2025-01-31 | Form returned and acknowledged | Closed | 2025-01-10
AP122 | January 2025 | 005/25 - Comments from members of the public | The clerk to add a review of the members of the working groups and committees at the next Parish Council meeting. | Clerk | 2025-02-06 | Deferred to the annual meeting in May | Closed | 2025-05-09
AP127 | January 2025 | 027/25 - Any Other Business | The clerk to arrange an emergency Parish Council meeting regarding the Road & Traffic project following feedback from Somerset Council to the brief provided on 24th December 2024. | Clerk | 2025-02-06 | The feedback will be provided at the Parish Council meeting on 12th Februray 2025 | Closed | 2025-02-05
AP128 | January 2025 | 027/25 - Any Other Business | The clerk is to ask the Somerset Council planning team if planning application Ref: 53/24/0006 has been amended | Clerk | 2025-02-06 | Checked planning application - found 53/24/0007 and emailed Councillors | Closed | 2025-02-05
AP124 | January 2025 | 014/25 - Weed control proposals | Clerk to research weed killer policies and practices used in other organisations. | Clerk | 2025-02-28 | On the agenda for 12th April 2025. No decision taken. Deferred. Discussed during 10/09/2025 PC Meeting - see new action AP171 | Closed | 2025-09-10
AP132 | February 2025 | 036/25 - Bishops Lydeard Leaflet | Cllr Lewin-Harris to confirm estimated costs of leaflet changes with the supplier. | Cllr Lewin-Harris | 2025-03-06 | On Hold | Open
AP134 | February 2025 | 041/25 - Digital Café Update | The clerk is to contact the people running the coffee mornings (Talking Café) in the Village Hall to find out more. | Clerk | 2025-03-06 | Meeting arranged for Thursday 5th March 2025. | Closed | 2025-03-05
AP135a | February 2025 | 043/25 - Approval to purchase new Noticeboards | Clerk to obtain alternative quotes for the noticeboards at Moorland Gate and opposite the school. | Clerk | 2025-03-06 | On the agenda for 12th April 2025 and 9th May 2025. Now on order. | Closed | 2025-05-30
AP123 | January 2025 | 012/25 - Community Skip Hire Costs | More information is required, and the Clerk is to research skip hire further and bring back to the council for approval. | Clerk | 2025-03-31 | On Hold | Open
AP126 | January 2025 | 024/25 - Poppy of Honour War Memorial Appeal | Cllr Lewin-Harris to order the Poppy of Honour War Memorial plaque via the link provided. | Cllr Lewin-Harris | 2025-03-31 | Completed and email received | Closed | 2025-03-17
AP129 | January 2025 | 027/25 - Any Other Business | The clerk is to investigate who in Somerset Council we need to contact regarding leasing the woodland between Minehead Road and the A358 bypass. | Clerk | 2025-03-31 | email sent to Charlie Field, Strategic Manager Estates, Somerset Council. Then to devolution email address | Closed | 2025-05-09
AP130 | February 2025 | 032/25 - Comments from members of the public | The clerk to contact the PCSO and ask if she can visit the location (streamside path) a few times a week | Clerk | 2025-03-31 | Completed and acknolwedged | Closed | 2025-03-09
AP131 | February 2025 | 034/25 - Civility and Respect | Clerk to complete an audit the Parish Council policies and procedures and identify gaps with the Civility and Respect requirements | Clerk | 2025-03-31 |  | Open
AP133 | February 2025 | 040/25 - Skate Park Trial Location Update | The clerk to research the potential costs (lease/ purchase cost, legal fees, maintenance fees etc.) of the Play Area by the station. | Clerk | 2025-03-31 | email sent to Julian Grant - then devolution team | Open
AP135 | February 2025 | 042/25 - Greenway Woodland | The clerk to provide information relating to the sale of the woodland (condition of the woodland, seller’s timescales and expected price, costs, etc.) | Clerk | 2025-03-31 | Meeting arranged for 3rd March 2025. Discussed at PC Meeting on 12th March. Costs etc. needed. Costs ready for mtg on 09/05/2025 | Closed | 2025-05-14
AP135b | February 2025 | 043/25 - Approval to purchase new Noticeboards | Clerk to purchase the noticeboard for the Quantock View phone box. | Clerk | 2025-03-31 | On the agenda for 12th April 2025 and 9th May 2025. Now on order. | Closed | 2025-05-30
AP136 | March 2025 | 063/25 Opening/ Closing Public Toilets | The clerk to enquire whether Fairy Dust Cleaning and Care Services would be willing to close the Public Toilets on Saturday, open and close them on Sundays and Bank Holidays (with the exception on Christmas Day and Boxing Day), clean the toilets on the additional days and if so at what cost. | Clerk | 2025-03-31 | email sent. Quote ready for next Parish Council meeting | Closed | 2025-03-31
AP137 | March 2025 | 066/25 Digital Café location | The clerk is to coordinate with the Digital Café representative and organise the meetings with the Talking Café Village Agent. | Clerk | 2025-03-31 | Planning to start on Thursday 3rd April 2025 | Closed | 2025-03-31
AP138 | March 2025 | 068/25 Asset Register | Clerk to add £1 minimum value, current value to the asset register, and restate last years AGAR Box | Clerk | 2025-03-31 | Completed | Closed | 2025-03-31
AP140 | March 2025 | 072/25 Finance | The clerk is to check the scope of work in the contract for the lengthsman. | Clerk | 2025-03-31 | Meeting held - document updated. Sent to councillors ahead of September meeting. | Closed | 2025-09-05
AP142 | March 2025 | 084/25 Any Other Business | The Chair and the Clerk will propose possible dates and venues for the Annual Parish Meeting and the Annual Meeting of the Council for agreement. | Chair & Clerk | 2025-03-31 | Annual Parish Meeting planned for 21st May. The Annual Meeting of the Council for 14th May | Closed | 2025-03-31
AP146 | April 2025 | 097/25 Correspondence | Clerk to raise the issue of the caravan parked on Taunton Road with the police. | Clerk | 2025-04-28 | Reported to PCSO via email on 14/04/2025. Response was no action can be taken. | Closed | 2025-04-15
AP139 | March 2025 | 069/25 Risk Register review | The clerk to prepare a separate MUGA Risk Assessment document | Clerk | 2025-04-30 | Does the ROSPA report cover this? New MUGA RA aprroved in Feb PC meeting. | Closed | 2026-02-11
AP141 | March 2025 | 084/25 Any Other Business | Clerk to request that Somerset Council maintain the bank that backs onto Kings Yard and Webbers on Mill Lane. | Clerk | 2025-04-30 | Raised with Somerset Council - Report reference: 841538 | Closed | 2025-04-11
AP147 | April 2025 | 098/25 Draft Emergency Plan | Cllr Roberts to bring more information to the next meeting | Cllr Roberts | 2025-05-07 | Delayed to July meeting | Closed | 2025-07-09
AP144 | April 2025 | 91/25 Approval to purchase new toilet roll holders for the Public Conveniences | The clerk to purchase two ETAL Lockable Double Toilet Roll Holder in Stainless Steel at £39.99 each. | Clerk | 2025-05-14 | Completed | Closed | 2025-05-09
AP154 | May 2025 | 129/25 CIL Update | The clerk is to send the link to the Somerset Council list of assets to the councillors. | Clerk | 2025-05-19 | email sent on 16/05/2025 | Closed | 2025-05-16
AP143 | April 2025 | 090/25 Opening/ Closing Public Toilets | The clerk to investigate alternative automated locking mechanisms for the toilet doors. | Clerk | 2025-05-31 | Quotation recived from Healthmatics. Added to July agenda | Closed | 2025-06-27
AP145 | April 2025 | 095/25 Authorisation of HSBC Bank Mandate to add Clerk/ RFO as a Signatory | Cllr Lewin-Harris to setup online banking with HSBC. The Clerk to be setup as administrator for the account | Cllr Lewin-Harris | 2025-05-31 | Forms rejected by HSBC and the clerk is not on Mandate. Council decision to close account on 11/06/2025. | Closed | 2025-06-11
AP148 | May 2025 | 119/25 and 120/25 Review of documents and policies | The clerk is to amend section 16.5 of the Finance Regulations and update all the documents with the ‘adopted date’ and ‘next review date’. | Clerk | 2025-05-31 | Completed and uploaded to website | Closed | 2025-06-18
AP149 | May 2025 | 123/25 Decision to Purchase Noticeboards | The clerk is to progress the noticeboard orders for signs with Arien Signs Ltd. | Clerk | 2025-05-31 | Signs now on order | Closed | 2025-06-02
AP150 | May 2025 | 126/25 Decision to Approve additional solar panels and brackets for the two SIDS | The clerk is to progress the order for two additional solar panels and brackets | Clerk | 2025-05-31 | Contcated Huga Barr to arrange deleivery. Now delivered. | Closed | 2025-05-30
AP157 | May 2025 | 141/25 AOB | The clerk to contact the lengthsman and request that the footpath is mowed which usually takes place in May and October. | Clerk | 2025-05-31 | Phonecall made on 19/05/2025 | Closed | 2025-05-19
AP151 | May 2025 | 126/25 Decision to Approve additional solar panels and brackets for the two SIDS | The clerk is to investigate if it is possible to collect speed data from the Speed Indicator Devices. | Clerk | 2025-06-11 | Discussed with Lengthman on 19/05/2025. Software downloaded and first SID data available. | Closed | 2025-10-29
AP152 | May 2025 | 127/25 New Lights for the Public Conveniences | The clerk is to obtain additional quotations for replacement lights in the Public Conveniences. | Clerk | 2025-06-11 | Meeting DJW Electrical on 09/07/2025. Peter Miller Electrical meeting arranged for 30/06/2025. Quotes obtained and on agenda for Aug PC meeting. | Closed | 2025-07-18
AP153 | May 2025 | 129/25 CIL Update | The clerk to express an interest in the Community Hall in Darby Way and request more information on the open space land at Hither Mead. | Clerk | 2025-06-11 | Email sent about Darby Way and email received confirming open space land which is on the agnda for the June meeting. | Closed | 2025-05-30
AP155 | May 2025 | 133/25 Finance | The clerk to amend the Regular Payments paper and look into stopping the gmail email account. | Clerk | 2025-06-11 | Regular Payments paper updated on 16/05/2025. SWS responded with cost to stop old email system and archive it. | Closed | 2025-07-06
AP156 | May 2025 | 141/25 AOB | The clerk to contact the farmer and arrange an onsite meeting regarding Whiskey Trail. | Clerk | 2025-06-11 | Meeting arranged for 8th July 2025 | Closed | 2025-06-18
AP159 | 2025-06-01 | 157/25 On Your Bike 2025 events proposal | Cllr Hunt to prepare a OYB paper including costs for the next meeting in July | Cllr Hunt | 2025-07-03 | Added to agenda. | Closed | 2025-07-06
AP166 | 2025-07-01 | 198/25 Sandhill Park Wood - decision to proceed with the purchase | The clerk is to liaise with the Sandhill Park Wood owners regarding the proposed offer. | Clerk | 2025-07-14 | Completed - Offer accepted | Closed | 2025-07-10
AP158 | 2025-06-01 | 156/25 Insurance renewal review | Cllr Lewin-Harris to establish a valuation for the War Memorial for insurance purposes | Cllr Lewin-Harris | 2025-07-31 |  | Open
AP160 | 2025-06-01 | 160/25 Authorisation of Vice Chair as a Signatory to Unity Bank account | The clerk to add a bank signatory review as an Agenda Item to a suitable Parish Council meeting | Clerk | 2025-07-31 |  | Open
AP161 | 2025-07-01 | 173/25 Decision on ‘Expression of Interest’ for the Hither Mead Open Space | The clerk is to communicate the decision that council does not wish to express and interest in the Hither Mead Open Space to Somerset Council. | Clerk | 2025-07-31 | Completed - email sent stating that the Parish Council does not wish to express and interest in the Hither mead Open Space. | Closed | 2025-07-15
AP162 | 2025-07-01 | 175/25 Approval to provide a mobile phone for the library | Cllr Rigby to follow up and request that Somerset Council continue to provide the telephone service as they do now. | Cllr Rigby | 2025-07-31 | Completed - see email from Somerset Council | Closed | 2025-07-15
AP163 | 2025-07-01 | 180/25 Approval to deactivate/ delete the old Facebook and Instagram accounts | The clerk will delete the old social media accounts and add provision of new social media accounts to a future agenda | Clerk | 2025-07-31 | Accounts scheduked for closure by 21 Aug 2025 | Closed | 2025-07-22
AP165 | 2025-07-01 | 191/25 Correspondence List | The clerk to provide the responses to the questions raised by email on 13 June 2025 to the member of the public. | Clerk | 2025-07-31 | Responses sent to the member of the public | Closed | 2025-07-15
AP167 | 2025-07-01 | 198/25 Sandhill Park Wood - decision to proceed with the purchase | The clerk is to confirm with Somerset Highways if South Drive has been adopted by the council. | Clerk | 2025-07-31 | South Drive is NOT on the adopted list provided by Somerset Council. Cllr Lewin-Harris has made enquiries and also understands that this is NOT an adopted road. | Closed | 2025-07-15
AP168 | 2025-08-01 | 216/25 Library Update | The clerk to circulate the draft Somerset Council Library Agreement to all councillors ahead of the September Parish Council meeting for review and comment. | Clerk | 2025-09-05 | Completed | Closed | 2025-09-10
AP169 | 2025-08-01 | 219/025 Lengthman’s monthly report | The clerk is to circulate to all councillors the current Lengthsman’s schedule of work for review and comment at a future Parish Council meeting. | Clerk | 2025-09-05 | Completed - new action AP170 | Closed | 2025-09-10
AP164 | 2025-07-01 | 182/25 Decision on opening and closing toilets | The clerk is to obtain quotations for the maintenance issues of the public conveniences | Clerk | 2025-09-30 | Replacement door quotation received from Healthmatic and approved at PC meeting in November. | Closed | 2025-12-10
AP179 | Oct-25 | 266/25 Correspondence List | The clerk to provide information that is available about councillor training as requested under an FOI. | Clerk | 2025-10-29 | FOI raised 02/10/2025. Report sent 29/10/2025 | Closed | 2025-10-29
AP170 | Sep-25 | 230/25 Review and approval of the Lengthsman’s Schedule of works | Lengthsman Schedule of Works to be updated and re-issued and reviewed again. | Clerk | 2025-10-31 | Added to March 2026 PC Meeting agenda. | Open
AP171 | Sep-25 | 231/25 Decision to spray the roadside, pavement and MUGA weeds and approval of quotation | Produce a Weed Control Policy for the Parish Council to consider and approve | Clerk | 2025-10-31 |  | Open
AP172 | Sep-25 | 242/25 Whisky Trail update | The clerk will meet the Lengthsman and Cllr Pattemore to survey the footpath and the Lengthsman will then be able to provide a proposal and quotation. | Clerk | 2025-10-31 | Meeting arranged for 6th October 2025 | Closed | 2025-10-06
AP173 | Oct-25 | 259/25 Review and approval of Back Stream environment study extent | The clerk is to liaise with the Wild Trout Trust and clarify the scope of the survey. | Clerk | 2025-10-31 | Scope agreed and survey completed | Closed | 2025-10-24
AP174 | Oct-25 | 260/25 Consider support of ‘Concealed Entrance’ driveway request | The clerk is to reply to the correspondent as agreed during the meeting. | Clerk | 2025-10-31 | email sent on 14/10/2025 | Closed | 2025-10-14
AP176 | Oct-25 | 266/25 Correspondence List | The clerk to reply to the member of the public regarding options to honour a local resident that had recently died. | Clerk | 2025-10-31 | email sent on 14/10/2025 | Closed | 2025-10-14
AP180 | Oct-25 | 267/025 Somerset Council Matters | The clerk to add the CO-OP planning application to the next Parish Council meeting agenda. | Clerk | 2025-10-31 | Added to agenda | Closed | 2025-11-07
AP175 | Oct-25 | 264/25 Finance | The clerk to add a review of the first draft of the 2026/27 budget to the agenda of the next Parish Council meeting in November. | Clerk | 2025-11-07 | Added to agenda | Closed | 2025-11-07
AP177 | Oct-25 | 266/25 Correspondence List | The clerk to add the Fiveways monthly report as a future agenda item. | Clerk | 2025-11-30 | Reviewed at November PC meeting - ref: 285/25 | Closed | 2025-11-12
AP178 | Oct-25 | 266/25 Correspondence List | The clerk is to establish a budget for a hearing loop ahead of the 2026/27 budget. | Clerk | 2025-11-30 | See also AP104 | Open
AP181 | Oct-25 | 268/025 Lengthman’s monthly report | The clerk is to review the format and content of the monthly Lengthsman report with the Lengthsman. | Clerk | 2025-11-30 | See also AP140, AP169, AP170. Added to March 2026 PC Meeting agenda. | Open
AP182 | Nov-25 | 277/25 Comments from members of the public | The clerk to add dog bins in the village as a future agenda item | Clerk | 2025-12-05 | Added to December PC meeting agenda - Expecting a CIL application from Moorlang Gate Committee. | Closed | 2025-12-05
AP184 | Nov-25 | 284/25 Review and recommendations regarding parking on Minehead Road | Cllr Rigby to request Somerset Highways to provide double yellow lines on both sides of Minehead Road at the junction with Station Road/ Mount Street. | Cllr Rigby | 2025-12-31 |  | Open
AP185 | Dec-25 | 305/25 Review of Dog Waste Bins | The clerk is to add a review of dog waste bins in the village to next month’s agenda. | Clerk | 2026-01-09 | Added to agenda | Closed | 2026-01-09
AP189 | Dec-25 | 320/25 Any Other Business | The clerk to add the Co-op planning application to the next Parish Council meeting agenda. | Clerk | 2026-01-09 | Added to agenda | Closed | 2026-01-09
AP190 | Dec-25 | 320/25 Any Other Business | The clerk to add a review of the draft weed control policy when available to the next Parish Council meeting agenda. | Clerk | 2026-01-09 | See also AP171 | Open
AP183 | Nov-25 | 280/25 Approval of estimate 1047 for the Lengthsman to clear the Whisky Trail path | The clerk is to obtain a second quotation for the clearance of the Whisky Trail path. | Clerk | 2026-01-31 | Connor from Kingfisher Tree Surgery was met onsite with Cllr Pattemore. Quotation recied and added to the March 2026 PC Meeting agenda. | Closed | 2026-11-05
AP186 | Dec-25 | 313/25 Correspondence List | The clerk to contact the Somerset Council Housing Revenue Account (HRA) team regarding the fencing that is falling over at Quantock View. | Clerk | 2026-01-31 | email sent. Awaiting a response. | Open
AP187 | Dec-25 | 317/25 Clerks Report and action tracker | The clerk is to obtain additional quotations for the Bus Shelter glass replacement. | Clerk | 2026-01-31 |  | Open
AP188 | Dec-25 | 317/25 Clerks Report and action tracker | The clerk is to request that repairs are made to the library facia and gutters by the building owners. | Clerk | 2026-01-31 | Email sent to Abbie and Solicitor | Closed | 2025-12-12

## 2026 Actions
Bishops Lydeard & Cothelstone Parish Council Action Tracker
Action Point | PC Meeting | Meeting Minutes Reference | Category | Action | Responsibility | Target Completion Date | Comments | Next Step | Status | Date Completed
AP191 | Jan-26 | 006/26 Review and approval of 2026/27 Precept |  | The clerk is to return the Precept demand to Somerset Council with a figure of £84,200 by the end of January 2026 deadline. | Clerk | 2026-01-31 | Completed |  | Closed | 2026-01-20
AP192 | Jan-26 | 009/26 Approval of new electronic toilet flush systems and cisterns for the public conveniences | Meeting RFI | The clerk is to investigate additional security measures for the public conveniences and bring back proposals for the council to consider. | Clerk | 2026-03-31 | New electrically controlled doors installed and set to unlock/ lock 0700/1900. | Cistern replacements at AP203 | Closed | 2026-03-19
AP193 | Jan-26 | 010/26 Review recommendations from Wild Trout Trust Advisory Visit Report of Back Stream |  | The clerk is to contact the Streamside Resident Group and request that they take on the recommendations from the Wild Trout Trust Advisory visit report. | Clerk | 2026-01-31 | email sent |  | Closed | 2026-01-20
AP194 | Jan-26 | 012/26 Planning Applications |  | The clerk is to contact the planning applications team about the concerns raised regarding parking and the request for an additional post box. | Clerk | 2026-01-31 | email sent |  | Closed | 2026-01-20
AP195 | Jan-26 | 014/26 Finance |  | The clerk to provide an update on the Public Conveniences Maintenance payments (code 33) incurred to date at the next meeting. | Clerk | 2026-02-11 | Paper prepared for Feb 2026 PC meeting |  | Closed | 2026-02-06
AP196 | Jan-26 | 018/026 Lengthman’s monthly report | Project | The clerk is to send out the current Lengthsman’s schedule of works and arrange for a review at a future Parish Council meeting. | Clerk | 2026-02-11 | See also AP170 and AP181. Added to the March 2026 PC Meeting agenda.At the March 26 meeting it was decided to form a Working Group to review the schedule and propose a new one. | Working Group to meet and formulate new schedule. | Open
AP197 | Feb-26 | 030/26 Confirmation of the list of sites from the Somerset Devolution team that the Parish Council would like to Express an Interest in |  | The clerk is to contact the Somerset Council Devolution team and confirm that the Parish Council wishes to express and interest in the Westbridge Way Play Area and the Woodland Walk - the one by the A358 area. | Clerk | 2026-03-11 | Email sent to the devolution team and acknowledged. |  | Closed | 2026-02-12
AP198 | Feb-26 | 031/26 Approval of the Developed Brief from Somerset Council for the Detailed Design of Site 14 |  | The clerk is to confirm approval of the developed brief to Somerset Council. | Clerk | 2026-02-16 | Signed Developed Brief sent and acknowledged. |  | Closed | 2026-02-12
AP199 | Feb-26 | 034/26 Approval to request that the Village Hall fenced play area including the under 5s play area is added to the new Dog Control Public Spaces Protection Order |  | The clerk is to request that the Westbridge Way Play Area near the station is added to the PSPO. | Clerk | 2026-03-01 | Email sent to consultation email address. |  | Closed | 2026-02-13
AP200 | Feb-26 | 035/26 Review of Litter and Dog Waste Bins in the village. | Meeting RFI | The clerk is to clarify the process to add new litter bins on Somerset Council’s land and to the schedule for emptying by Somerset Council. | Clerk | 2026-03-30 | Not started |  | Open
AP201 | Feb-26 | 039/26 Correspondence List. |  | Clerk to forward emails relating to the reduction in the grant received from the War Memorial Trust following the cleaning of the War Memorial by SSH Conservation. | Clerk | 2026-03-11 | Emails forwarded to councillors. |  | Closed | 2026-02-13
AP202 | 2026-03-01 | 052/26 - Approval of the quotation to replace the library strip lights | Maintenance | Arrange Strip Light replacement | Clerk | 2026-04-17 | Voicemail to Pete Miller 17/3. No response. Follow up email sent 19/3 requesting work coincide with Library facia refurbishment. Confirmed as 15 April. | Installation to be completed 15 Apr 26 | Open
AP203 | 2026-03-01 | 053/26 - Approval to replace the leaking toilet cisterns | Project | Toilet cistern replacement - Healthmatic. Water Bill enquiries regarding possible leak. C1 Meter verification with Wessex Water | Clerk | 2026-03-31 | Healthmatic asked to carry out cistren replacements. Water Meter Inspection 17 Mar 26 1300-1400. Confirmed no leak. Confirmed Surgery not connected to supply. Unable to confirm 4 Mount Street not connected although found their meter. | Need new vote at PC Meeting before confirming date from Healthmatic for installation | Open
AP204 | 2026-03-01 | 054/26 - Review and approval of the Whisky Trail quotations | Project | Obtain further quotes for a modified solution of the installation (just posts), Try and confirm who owns the land, Report the lack of signage for the footpath with Somerset Council, and defer this decision to a later meeting. | Clerk |  | Footpath issues reported to SC - 85906, 85907. RoW Warden - John Melrose | Awaiting SC action. | Open
AP205 | 2026-03-01 | 055/26 - Review of search results for the purchase of Sandhill Park Woodland | Meeting RFI | Query Right to Park on South Drive with Solicitor | Clerk |  | OTBE - Solicitor sent Report on Title. Whilst it oesn't address parking specifically, it does state that we would have access along "Acorn Road" | Not discussed by PC yet | Open
AP206 | 2026-03-01 | 064/26 - Finance ( Roads Project Cothelstone Hill) | Project | Request Signage for Pound Lane Wall directing pedestrian traffic to footpath through Darby Way | Clerk |  | Investigated which SC department would deal with this - no luck | Ask Cllr Rigby??? Put up sign anyway?? | Open
AP208
AP209
AP210
AP211
AP212
AP213
AP214
AP215
AP216
AP217

## Internal Audit Actions
Recommendation no. | Detail | To be completed by | Date completed | Notes
B.1 | Dealing with invoices received: Invoices should be date stamped with their receipt date and the Clerk should initial the amounts to indicate that these have been checked for accuracy. | Parish Clerk | 2025-05-31 | New date stamp bought and invoices now checked and stamped.
C.1 | Risk Management: The MUGA and other outdoor spaces must be added to the Risk Assessment document. The risks must be identified and rated and control measures agreed. This document must be explicitly approved by the Full Council. | Parish Clerk | 2026-02-11 | MUGA Risk Assessment completed by RoSPA. New MUGA Risk Assessment approved at the Feb 2026 PC Meeting.
C.2 | Bank account administration: The Clerk must be made the service administrator for all bank accounts. Councillors should have the ability to view accounts and authorise payments but not be able to set up payments as this is the responsibility of the Clerk in his role as Responsible Financial Officer. | Parish Clerk | 2025-10-31 | Unity Trust online form completed. Now signed and returned. Clerk now have administation rights.
D.1 | Budget position reports: These should be presented to the Council at least quarterly. | Parish Clerk | 2025-09-10 | Now on the agenda monthly
E.1 | Library lease: A formal lease should be drawn up between the Council and the owner of the library premises. | Parish Clerk |  | Delayed pending completion of probate for C Back.
G.1 | Contract of employment: It is strongly recommended that the Council adopts the NALC model contract of employment for the Clerk. | Parish Clerk | 2025-09-03 | Document prepared. Approved at Staffing Committee Meeting on 3rd September 2025.
H.1 | Investments: The Council should adopt an investment policy to ensure that it is realising the best return on the balances it is holding. | Parish Clerk | 2025-10-08 | Document produced and on the agenda for PC meeting on 8th October 2025. Adopted.
L.1 | Publication requirements: The Council should review the information it publishes to ensure it complies with the model publication scheme provided by the Information Commissioner’s Office. | Parish Clerk | 2025-09-02 | Publication List produced and uploaded to website under Policies
jjzz